## RAB
SMK NEGERI 4 MALANG
JURUSAN TEKNIK ELEKTRONIKA
UNIT PELAYANAN DAN JASA MEKATRONIKA
Jl. Tanimbar 22 Malang 65117 ( (0341) 353798, Fax (0341) 363099
e-mail : mekatronika.smkn4malang@gmail.com
RANCANGAN ANGGARAN BIAYA
SMA N 4 MALANG
| No | Nama | Satuan | Qty | Harga Satuan | Total | Keterangan
| (A+B+C+D+E+F) | SMA N 4 MALANG | set | 1 |  | 17272674.18
| A | Nama Ruang PVC 30 x 15 cm 1pax=7pcs | pax | 6 | 1019569.25 | 6117415.5
| B | Logo Provinsi dan Sekolah W40cm | pcs | 2 | 652410 | 1304820
| C | Logo Sekolah W80cm | pcs | 1 | 1598235 | 1598235
| D | Huruf Timbul H30cm pax=4huruf | pax | 2.75 | 2104597.7011 | 5787643.6782
| E | Neon Text "Merdeka Belajar" | pax | 1 | 1221828 | 1221828
| F | Neon Text "Sekolah Penggerak" | pax | 1 | 1242732 | 1242732
Malang,…………………………….
Anggoro Dwi Nur R., S.Pd
NIP.

## TLP
SMK NEGERI 4 MALANG
JURUSAN TEKNIK ELEKTRONIKA
UNIT PELAYANAN DAN JASA MEKATRONIKA
Jl. Tanimbar 22 Malang 65117 ( (0341) 353798, Fax (0341) 363099
Website : www.smkn4malang.sch.id ¦ e-mail : mail@ smkn4malang.sch.id
TIME LINE PROJECT
Alga Farm
| # | Kegiatan |  | PIC | Durasi (H) |  |  | Mulai | Selesai | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28
 | time axis 2022-02-21 to 2022-04-03
[6 empty] | Hari Kerja | Akhir pekan | time axis 2022-02-21 to 2022-04-03
| 1 |  |  | 1 | 15 | TRUE | FALSE | 2022-02-21 | 2022-03-27 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1 | Pembelian Elektronik kendali | 1 | 10 | TRUE | FALSE | 2022-02-21 | 2022-03-06 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.2 | Pembuatan Elektronik Kendali | 1 | 10 | TRUE | FALSE | 2022-03-07 | 2022-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.3 | Perakitan Elektronik Panel | 1 | 5 | TRUE | FALSE | 2022-03-21 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 |  |  | 1 | 15 | TRUE | FALSE | 2022-02-21 | 2022-03-27 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1 | Pembelian Peralatan Mekanik | 1 | 10 | TRUE | FALSE | 2022-02-21 | 2022-03-06 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.2 | Pembuatan Peralatan Mekanik | 1 | 10 | TRUE | FALSE | 2022-03-07 | 2022-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3 | Perakitan Peralatan Mekanik | 1 | 5 | TRUE | FALSE | 2022-03-21 | 2022-03-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 |  |  | 2 | 5 | TRUE | FALSE | 2022-03-27 | 2022-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| 4 |  |  | 0 | 1 | TRUE | FALSE | 2022-04-03 | 2022-04-03 09:36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## TLP PRIVATE
| Mulai: | 2023-01-31 | Mulai |  |  |  | Selesai: | 2023-02-28 | [6 empty] | Tampilkan Pekan ke | 1
# | Kegiatan |  | PIC | Durasi (P) |  |  | Mulai | Selesai
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91
[5 empty] | Hari Kerja | Akhir pekan |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
1 | Nama Ruang PVC 30 x 15 cm 1pax=7pcs |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | membeli bahan |  | 3 |  |  | 2023-02-07 | 2023-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pengerjaan pvc | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finnishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Logo Provinsi dan Sekolah W40cm |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Membeli bahan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pengerjaan akrilik | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pemesanan stiker | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finnishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Logo Sekolah W80cm |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Membeli bahan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pengerjaan akrilik | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pemesanan stiker | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finnishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Huruf Timbul H30cm pax=4huruf |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | membeli bahan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pengerjaan akrilik | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Neon Text "Merdeka Belajar" |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | membeli bahan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pengerjaan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Neon Text "Sekolah Penggerak" |  | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | membeli bahan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | pengerjaan | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | finishing | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Selesai = [Mulai]+(7*[Durasi (P)])

## Actual TLP
| Mulai | 2023-01-31 | [12 empty] | Tampilkan Pekan ke | 0
[9 empty] | 0 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17
# | Kegiatan |  | PIC | Durasi (H) |  |  | Mulai | Selesai | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22
 | time axis 2023-01-23 to 2023-05-28
[5 empty] | Hari Kerja | Akhir pekan | time axis 2023-01-23 to 2023-05-28
1 | #REF! |  | 1 | 105 | TRUE | FALSE | 2023-01-31 | 2023-03-01 19:12
|  |  | 1 | 21 | TRUE | FALSE | 2023-01-31 | 2023-02-28 09:36 | 2023-01-28: 1; 2023-01-30: 1; 2023-01-31: 0; 2023-02-01: 0; 2023-02-02: 1; 2023-02-03: 1; 2023-02-06: 1; 2023-02-08: 1; 2023-02-20: 1; 2023-02-21: 1; 2023-02-22: 1; 2023-02-23: 1; 2023-02-24: 1; 2023-02-27: 1; 2023-02-28: 1; 2023-03-01: 1; 2023-03-02: 1; 2023-03-03: 1; 2023-03-06: 1; 2023-03-07: 1; 2023-03-08: 1; 2023-03-09: 1; 2023-03-10: 1
|  |  | 1 | 17 | TRUE | FALSE | 2023-01-31 | 2023-02-22 19:12 | bar: 2023-02-06 to 2023-02-10; 2023-02-13 to 2023-02-17; 2023-02-23 to 2023-02-24; 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
|  |  | 1 | 5 | TRUE | FALSE | 2023-02-23 19:12 | 2023-03-01 19:12 | bar: 2023-03-13 to 2023-03-17
|  |  | 1 | 10 | TRUE | FALSE | 2023-01-31 | 2023-02-13 | bar: 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24
|  |  | 1 | 15 | TRUE | FALSE | 2023-01-31 | 2023-02-22 08:10 | 2023-02-17: 1; 2023-02-18: 0; 2023-02-19: 0; 2023-02-20: 1; 2023-02-21: 1; 2023-02-22: 1; 2023-02-23: 1; 2023-02-24: 1; 2023-02-27: 1; 2023-03-15: 1; 2023-03-16: 1; 2023-03-17: 1; 2023-03-27: 1; 2023-03-28: 1; 2023-03-29: 1; 2023-03-30: 1; 2023-03-31: 1
|  |  | 1 | 0 | TRUE | FALSE | 2023-02-23 19:12 | 2023-02-22 19:12
|  |  | 1 | 15 | TRUE | FALSE | 2023-02-23 19:12 | 2023-03-15 19:12 | bar: 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07
|  |  | 2 | 22 | TRUE | FALSE | 2023-03-01 19:12 | 2023-03-31 14:24 | 2023-03-17: 1; 2023-03-18: 0; 2023-03-20: 1; 2023-03-21: 1; 2023-03-22: 1; 2023-03-23: 1; 2023-03-24: 1; 2023-03-27: 1; 2023-03-28: 1; 2023-03-29: 1; 2023-03-30: 1; 2023-03-31: 1; 2023-04-03: 1; 2023-04-04: 1; 2023-04-05: 1; 2023-04-06: 1; 2023-04-07: 1; 2023-04-10: 1; 2023-04-11: 1; 2023-04-12: 1; 2023-04-13: 1; 2023-04-14: 1; 2023-04-17: 1
|  |  | 0 | 0 | TRUE | FALSE | 2023-04-01 14:24 | 2023-03-31 14:24

## RAB PRIVATE
# | Nama Barang | Satuan | Qty | Harga Satuan | Harga Total | Harga Satuan [Private] | Harga Total | Informasi Toko atau Barang
1.5
| SMAN 4 MALANG |  | 1 | 17272674.18 | 17272674.18 |  | 11515116.12
A | Nama Ruang PVC 30 x 15 cm 1pax=7pcs | pax | 6 | 1019569.25 | 6117415.5 | 679712.8333 | 4078277
| PVC Board 3MM 60 x 80 cm | pcs | 1.8842 | 87750 | 165335.625 | 58500 | 110223.75 | https://www.tokopedia.com/naesshop/pvc-foam-board-3m-papan-lembaran-60cm-x-80cm?extParam=whid%3D4865630
| pylox hitam flat | pcs | 1.8842 | 49350 | 92983.625 | 32900 | 61989.0833 | https://www.tokopedia.com/smarttools/cat-semprot-pylox-black-flat-black-doff?extParam=ivf%3Dfalse%26src%3Dsearch
| Jasa potong | cm2 | 9600 | 75 | 720000 | 50 | 480000
| gantungan | pax | 1 | 41250 | 41250 | 27500 | 27500 | https://www.tokopedia.com/kios66/gantungan-kunci-besi-gantungan-besar?extParam=ivf%3Dfalse&src=topads
B | Logo Provinsi dan Sekolah W40cm | pcs | 2 | 652410 | 1304820 | 434940 | 869880
| Akrilik 2 mm 40 x 60 cm | pcs | 0.585 | 471000 | 275535 | 314000 | 183690 | https://www.tokopedia.com/aeol/akrilik-putih-susu-3mm-100x100-dan-100x200-100x100?extParam=whid%3D2074901
| Sticker vinyl 100 x 100 cm | pcs | 1 | 157500 | 157500 | 105000 | 105000 | https://www.tokopedia.com/kuynyetak/cetak-stiker-vinyl-meteran-indoor-outdoor-print-stiker-meteran-laminasi-doff?extParam=ivf%3Dfalse&src=topads
| jasa potong akrilik | cm2 | 5850 | 37.5 | 219375 | 25 | 146250
|  |  |  | 0 | 0 |  | 0
C | Logo Sekolah W80cm | pcs | 1 | 1598235 | 1598235 | 1065490 | 1065490
| Akrilik 2 mm 80 x 100 cm | pcs | 1.785 | 471000 | 840735 | 314000 | 560490 | https://www.tokopedia.com/aeol/akrilik-putih-susu-3mm-100x100-dan-100x200-100x100?extParam=whid%3D2074901
| Sticker vinyl 100 x 100 cm | pcs | 1 | 157500 | 157500 | 105000 | 105000 | https://www.tokopedia.com/kuynyetak/cetak-stiker-vinyl-meteran-indoor-outdoor-print-stiker-meteran-laminasi-doff?extParam=ivf%3Dfalse&src=topads
| jasa potong akrilik | cm2 | 16000 | 37.5 | 600000 | 25 | 400000
|  |  |  | 0 | 0 |  | 0
D | Huruf Timbul H30cm pax=4huruf | pax | 2.75 | 2104597.701 | 5787643.678 | 1403065.134 | 3858429.119
| Akrilik 2 mm 80 x 100 cm | pcs | 3.8314 | 471000 | 1804597.701 | 314000 | 1203065.134 | https://www.tokopedia.com/aeol/akrilik-putih-susu-3mm-100x100-dan-100x200-100x100?extParam=whid%3D2074901
| jasa potong akrilik | cm2 | 8000 | 37.5 | 300000 | 25 | 200000
|  |  |  | 0 | 0 |  | 0
E | Neon Text "Merdeka Belajar" | pax | 1 | 1221828 | 1221828 | 814552 | 814552
| neon flex | pcs | 1.456 | 100500 | 146328 | 67000 | 97552 | https://www.tokopedia.com/funminishop/lampu-neon-flex-selang-12v-dc-neonflex-12v-neonflexible-led-neonsign-warmwhite?extParam=ivf%3Dfalse&src=topads
| jasa potong akrilik | cm2 | 24000 | 37.5 | 900000 | 25 | 600000
| PSU 12 V | pcs | 1 | 175500 | 175500 | 117000 | 117000 | https://www.tokopedia.com/dreamtechno/power-supply-12v-40a-murni-barang-terjamin?extParam=ivf%3Dfalse&src=topads
|  |  |  | 0 | 0 |  | 0
F | Neon Text "Sekolah Penggerak" | pax | 1 | 1242732 | 1242732 | 828488 | 828488
| neon flex | pcs | 1.664 | 100500 | 167232 | 67000 | 111488 | https://www.tokopedia.com/funminishop/lampu-neon-flex-selang-12v-dc-neonflex-12v-neonflexible-led-neonsign-warmwhite?extParam=ivf%3Dfalse&src=topads
| jasa potong akrilik | cm2 | 24000 | 37.5 | 900000 | 25 | 600000
| PSU 12 V | pcs | 1 | 175500 | 175500 | 117000 | 117000 | https://www.tokopedia.com/dreamtechno/power-supply-12v-40a-murni-barang-terjamin?extParam=ivf%3Dfalse&src=topads
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0
|  |  |  | 0 | 0 |  | 0

## Actual RAB
# | Nama Barang | Satuan | Qty | Harga Satuan | Harga Total | Harga Satuan [Private] | Harga Total | Informasi Toko atau Barang
2.5
| Alga Farm |  | 1 | 7616375 | 7616375 |  | 0
A | Tahap 1 |  |  | 7616375
| mentari putri | toko | 1 | 1458000 | 1458000
| Fani Aluminium Profile | toko | 1 | 1287500 | 1287500 |  |  |  | https://drive.google.com/file/d/1I_rxOPki1wfIgF-MOjRPG3cpsuawYNoN/view?usp=drivesdk
| CENTI Store | toko | 1 | 2238700 | 2238700 |  |  |  | https://drive.google.com/file/d/1IbE9tzxZQBz5YcGqj67EfU9qH0HjoWx3/view?usp=drivesdk
| 3Din | toko | 1 | 265700 | 265700 |  |  |  | https://drive.google.com/file/d/1Ni_BIrc4MdH-qJBwM0Cyk9pz9n4pvnTl/view?usp=drivesdk | https://drive.google.com/file/d/1bf6lwAAW2Fec9JQ-WTHDw3TW4xuOAk01/view?usp=drivesdk
| Toko Hasil | toko | 1 | 66400 | 66400 |  |  |  | https://drive.google.com/file/d/1TjoUJo7eUA1iyog1gzZ5nUM2V0UsaylL/view?usp=drivesdk | https://drive.google.com/file/d/1bAUEGxhbt0Yoz-uui91iYD43gRnRLkGy/view?usp=drivesdk | https://drive.google.com/file/d/17yywVVlzjzFnyIIZNMOfahggIKSafhCw/view?usp=drivesdk
| Abadi Kaca | toko | 1 | 75000 | 75000 |  |  |  | https://drive.google.com/file/d/189qAi25sedV7ORAhXJQs5ZyL8Fy9tbfc/view?usp=drivesdk
| DIY | toko | 1 | 20000 | 20000 |  |  |  | https://drive.google.com/file/d/1bAUEGxhbt0Yoz-uui91iYD43gRnRLkGy/view?usp=drivesdk
| BB | toko | 1 | 105000 | 105000 |  |  |  | https://drive.google.com/file/d/1bAUEGxhbt0Yoz-uui91iYD43gRnRLkGy/view?usp=drivesdk
| spare part jakarta | toko | 1 | 101500 | 101500 |  |  |  | https://drive.google.com/file/d/1be3yEveQJDeOo-TWb9DcVPC38TWOyFgc/view?usp=drivesdk
| raja cell | toko | 1 | 615000 | 615000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| glodok | toko | 1 | 238275 | 238275 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| anugrah | toko | 1 | 220800 | 220800 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| delta | toko | 1 | 95000 | 95000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| hasil | toko | 1 | 22500 | 22500 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXjj
| digpart | toko | 1 | 179000 | 179000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| bangunan | toko | 1 | 50000 | 50000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| bb | toko | 1 | 45000 | 45000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| dinamika | toko | 1 | 2000 | 2000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| golden | toko | 1 | 6500 | 6500 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| delta | toko | 1 | 65000 | 65000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| hasil | toko | 1 | 31500 | 31500 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| digpart | toko | 1 | 93000 | 93000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| bb | toko | 1 | 90000 | 90000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| anugrah | toko | 1 | 150000 | 150000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
| haebot | toko | 1 | 95000 | 95000 |  |  |  | https://drive.google.com/drive/folders/1675LA5Lv3MeT3GqUqfeGf0osW4WPUOXj
|  | toko | 1 |  | 0
|  | toko | 1 |  | 0
|  | toko | 1 |  | 0
|  | toko | 1 |  | 0
|  | toko | 1 |  | 0

## absensi
Kegiatan: ...........................................................................................
Tanggal: ...............................................................................................
NAMA

## Invoice
UPJ MEKATRONIKA SMKN 4 MALANG
Jl. Tanimbar 22 ,Malang 65117
( (0341) 353798, Fax (0341) 363099
Kuitansi
Tanggal Transaksi 10 /09/2022
Kuitansi untuk |  | Diterima oleh |  | No Kuitansi #
Biologi Universitas Negeri Malang Jl. Semarang No.5 Kota Malang, Jawa Timur 65145 |  | UPJ SMKN 4 Malang a/n Anggoro Dwi Nur R |  | 20220910
|  | Project |  | Tanggal Pembayaran
|  | Otomasi Mesin Alga |  | 2022-10-09
Deskripsi |  |  |  | Harga Unit | Total Harga
Otomasi Mesin Alga |  |  |  | 17272674.18
Pembayaran DP Otomasi Mesin Alga |  |  | 56.45% |  | 9750000
Notes: Sisa pembayaran |  | 7522674.178 |  | Subtotal | 9750000
9750000